Project Milestones and Timeline for EU European Semester Alliance

|  | EU LEVEL ALLIANCE |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Main Milestones |  | Jan-March | April - June | July - Sept | Oct-Dec |
| Steering Group meetings based on Terms of Reference | Policy | Agree Terms of Reference for SG: 04/03 Initial planning SGs SG: February 14 SG: March 4 SG: March 31 | SG: 22 May | SG: 11 Sept . | SG: 21 October SG: 27 November |
|  | Comms | 31/03/2014 - Discussion and agreement on: - Comms strategy - Logo/visual - PPT & letter templates - Blog content and social media - Creating Alliance communications ad-hoc group with Comms officers with the Coordinator of the Alliance Members, following up and monitoring the results of the strategy | Semester Alliance comms group – proposal to meet on strategy and implementation, blog content and update, involvement of Alliance members (either 13 or 15/05) |  |  |
| 2 Alliance Meetings |  | 1st Alliance Meeting: 14 Feb |  |  | 2nd Alliance Meeting: 27 November. |
| Joint cross-sectoral Tool Kit for engaging in national Semester |  | Scoping of Tool Kit: 10 March Call for proposals: 13 March Selection of sub-contractor: 31 March | Final Draft: 15 May Publication: 7th June |  |  |
|  | Comms |  | - Final draft sent to Comms for layout 23/05 - Printed out 06/06 |  |  |
| 1 Capacity Building seminar involving national pilots. |  | Scope Capacity Building Seminar: 31st March | Finalize Programme with national pilot alliances: 1st May | Delivery of Capacity Building with national pilots: 17th June | Report of Capacity Building Sept 2014. |
| EU Advocacy and consultative meetings |  | Establish planning for consultative meetings with ECON/EMP/ ENV: 31st March | Regular | Regular meetings | Regular meetings. |
| Joint Reports - on CSRs |  | Agree framework and produce 1) short 2014 Alternative CSR report based on inputs from national members 21 March | 31 March: Dissemination with PR Disseminate 1) Report |  |  |
|  |  | Report laidout by Comms for Semester Alliance launch | Report disseminated through website, blog, social media with PR at 07/04 SA launch |  |  |
| - Joint Report on NRPs/Semester |  | NRPs/Semester Process/ Key Messages Scoping and Background Note | Selection of consultant: 30 April Develop outline/methodology 30 May Send out questionnaire 1st June Collect input: 30 June | Produce 1st Draft 30 August 2nd Draft: Mid September Finalize draft/lay-out and proofing: End September Mid October: printed publication. |  |
| 2 Cross-party hearings on CSRs and on Semester | Policy |  | 07/04/2014 Launch of the Alliance: 1 Cross-party hearing on CSRs 2014 to present CSR proposals | Establish contacts with new EP and develop cross-party hearing | Delivery of 2nd Cross-party hearing with participation of national members/pilots. |
|  | Comms |  | - Visual identity adopted - Launch of the blog + dedicated website area on all websites - Press release and invitation to journalists the Hearing/Event 07/04 - Provide leaflet/mission statement and package, what the alliance is; main actions give visibility to alliance members - Social media activity fed and relayed by members |  |  |
| Set up 3 National Cross-Sectoral Pilot Alliances |  | Develop framework and selection process for 3 pilots: 3 March Select 3 pilots: 31 March | Finalize Work programme and Delivery of national pilots: 1st May | Capacity Building Seminar as above: 17 June | Delivery and Evaluation of Work Programme: Nov/Dec: 2014 |
| Evaluation Strategy |  | Design Evaluation Strategy with SG: 31 March | Implement | Implement | Dec: Evaluation report |
|  | NATIONAL PILOT INITIATIVES |  |  |  |  |
| Main Milestones |  | Jan-March | April-June | July - Sept | October-December |
| Selection of 3 coordinators/ pilots |  | Background Doc and Call for Application agreed and sent out: 4th March Deadline: 28 March Selection: 31 March | Start of Contract: 1 April |  |  |
| Agreement of Work Programme |  |  | By 1 May |  |  |
| Launch of National Alliance |  |  | From 1 May |  |  |
| Organization of regular national alliance meetings |  |  | X | X | X |
| Participation in Capacity Building Workshop |  |  |  | 17 June |  |
| Coordinated input and review of NRPs |  |  | X | X | X |
| Monitoring CSR implementation and joint proposals for CSRs |  |  |  | X | X |
| Contribution to EU report |  |  | Input to proposed outline: methodology and report. Response to questionnaire/June- July | Comments on draft report |  |
| National Advocacy Event |  |  |  | X | X |
| Participation in EU advocacy event |  |  |  | October |  |
| Meetings with National Govts, ESOs |  |  |  | X | X |
| Communication Action Plan |  |  | May 30 | Delivery | Evaluation: Nov |
| Evaluation Report according to agreed framework |  |  |  |  | Nov |

List of deliverables per type:

Press releases 1° 07/04/2014 – launch of the Semester Alliance and CSR joint proposals report