Doc 6A Exco March 2016

**EAPN Restructuring Time Line**

|  |  |
| --- | --- |
| **Actions** | **Calendar** |
| Presentation (first draft) and first discussion at the October 2015 ExCo | 10th of October 2015 |
| Period for consultation and discussion by the National Network’s, European Organization’s and EAPN Staff. Contributions should be sent to the Bureau and Acting Director. | 10th October – 31 January 2016 |
| All contributions put together in one document and made available on members room | 2 February |
| Second draft, based on contributions and highlighting commonalities and divergence in the inputs received, should be sent to everyone | Sent to members 19 Feb |
| Second Draft discussed during March Exco. Methodology for discussion to be worked out.  | 11 – 12 March |
| Third Draft prepared following discussions at the Exco,  | Sent to members 25 March |
| Comments on third Draft sent to Bureau and Acting Director | 15 April 2016 |
| Third Draft and Comments received discussed at Bureau Meeting  | End April beginning May |
| Fourth Draft developed on the basis of Bureau discussion and sent to members.  | Mid May |
| Fourth Draft discussed at Exco Meeting in June  | Mid June |
| Fifth and final Draft prepared on the basis of the June Exco discussion | End June |
| Members can send formal amendments to be discussed and voted at the GA.  | Deadlines for receiving amendments, in line with the Statutes and Standing Orders, will be set in the Agreed Procedures for the GA Document (This document will be approved at the June Exco)  |
| Discussion and approval at the GA 2016 (The final proposal should ensure that it is possible to be coherent with the likely budgets available to EAPN in the coming years) | Early Oct 2016 |