Annex 1

Template for the Annual Work Programme

Cover Page

The key role of the Annual Work Plan is to plan activities aimed to achieve the strategic objectives at a more detailed level.

Please read and follow the instructions carefully. Please write your text in the grey areas.

Name of the Partner Organisation:  European Anti-Poverty Network (EAPN)                            
Framework Partnership Agreement Reference number:  VS/2013/0466

Annual Work Programme 2016

1. Detailed activity planning

Please develop on the key activities as set out in Chapter 6 of the Quadrennial Strategic Plan and provide a detailed list of strategic objectives, outcomes and outputs to be produced under this year work programme as well as planned activities which will lead to their delivery.

The template for the detailed activity planning is divided in two parts, one for applicants in area 1 and one for applicants in area 2.

- Area 1: EU-level networks active in the promotion of social inclusion and poverty reduction

- Area 2: EU-level networks active in the promotion of microfinance and social enterprise finance

For each of the 4 area-specific priorities indicated in the call the Annual Work Programme contains:

### strategic objectives: the list of relevant strategic objectives that have been identified in the quadrennial strategic action plan and that are linked to the realisation of a specific priority

### outcomes: outcomes shall contribute to the strategic objectives; they are achieved by one or more outputs

### outputs: outputs are the products/ results of undertaken activities; contributing to concrete outcomes (Please quantify outputs where possible e.g. by indicating number of meetings, publications, etc.)

### activities: the things that must be done to achieve the outputs (List all activities including monitoring and evaluation to be undertaken during the year.).

### the timeframe for undertaking the planned activities (Please indicate relevant months)

### the resources to be provided for each activity and planned budget. (List the indicative total amount of all related costs by categories, including staff costs.

### Information should be structured in the following way:

### Staff costs: post/ number of working days

### Travel costs: no of persons travelling, estimated travel cost, per diems or catering (in case of a bigger event you could refer to the relevant line in the budget section)

### Services: type of service, unit costs, total

### Administration costs (if directly related to the work programme): type of cost, unit cost, total

### Other costs: type of cost, unit cost, total

### Please note that the costs indicated in the budget should correspond to the costs indicated in the work programme e.g. in terms of working days for staff or number of travels.)

Some of the outputs and activities foreseen by the applicant might contribute to different priorities. It is highly recommended to mention those activities only once, preferably under the most relevant priority for this specific activity. Under other priorities a short reference can be inserted if needed.

Use the Table below. Please insert/delete (merge/split) lines as required.

## annual Work Plan template

##### Year _____2016_______

Area 1. EU-level networks active in the promotion of social inclusion and poverty reduction

For each of the 4 priorities indicated in point IV of the call VP/2015/010, 
the annual work programme contains the list of strategic objectives and expected outputs

| Priority 1: Support the development, implementation, monitoring and evaluation of initiatives undertaken towards the policy objectives of Europe 2020 Strategy and in particular the Social Investment Package and the Political Guidelines of the new Commission. Support the main EU driven processes such as the Open Method of Coordination (OMC) on social protection and social inclusion and the European semester. |
| --- |
| Priority 1 is delivered through EAPN’s Strategic Objective 1.1: EAPN will work to ensure that the Europe 2020 strategy, the Platform against Poverty and the Social Inclusion strategy (Social OMC), the Employment Policy (European Employment Strategy) and Cohesion Policy (Structural Funds) deliver progress to: effectively mainstream social concerns, reduce poverty and inequality and ensure that public policies, programmes and intervention reach people living in poverty, including the most disadvantaged. And through Specific Objectives 1, 2, 3 and 4: Europe 2020 and Cohesion Objectives for 2016. Defend the poverty target and EAPN proposals for the Mid-Term Review of Europe 2020 in the Semester, monitor trends on poverty and get new EU commitments to reduce poverty through an integrated antipoverty strategy based on integrated Active Inclusion and Social Investment in quality jobs, services and social protection. Work to ensure that the minimum 20% of the ESF ear-marked for antipoverty is implemented, and support greater NGO engagement in the monitoring committees and in delivery; input to the Review of the Multi-annual Framework to ensure better budgets for poverty. Contribute to proposals to make Progress on EU social standards, specifically through proposals for an EU social protection floor, adequate minimum income and minimum wages. Build capacity and achieve more meaningful and impactful engagement of stakeholders in Europe 2020/ and the European Semester and other policy processes at EU and national level. |
| STRATEGIC OBJECTIVES in order to meet PRIORITY 1 | OUTCOMES | OUTPUTS (please quantify) | ACTIVITIES | TIMEFRAME PER ACTIVITY (mm/yy) | RESSOURCES AND PROVISIONAL BUDGET PER ACTIVITY (detailed breakdown) |
| Strategic Objective 1.1.: EAPN will work to ensure that the Europe 2020 strategy, the Platform against Poverty and the Social Inclusion strategy (Social OMC), the Employment Policy (European Employment Strategy) and Cohesion Policy (Structural Funds) deliver progress to: effectively mainstream social concerns, reduce poverty and inequality and ensure that public policies, programmes and intervention reach people living in poverty, including the most disadvantaged. Specific Objectives 1 and 4. | Stakeholders at national and European levels to gain a better understanding of the Europe 2020 process and its impact at national level. Improved mutual learning and review of policy trends and impact on poverty. | 2 EUISG meetings – each for two and a half days) of EAPN’s EU Inclusion Strategies Group (EUISG) with representatives from 31 national networks and 5 European Organizations. The second meeting in October meeting will be organized with the Policy Conference. (see later section) [Outputs will include agendas/minutes, and also presentations and evaluations.] | Preparation, organization of meetings involving EUISG Steering Group. Preparation of agendas, background documents, organization of logistics of meetings. Delivery of Meetings/ Evaluation. Follow up, Minutes. Ongoing contact and communication with members. | Dec-Jan, Aug-Sept February and October. March and November. | Travels 64 persons: 14080 Euro/Subsistence 32 persons x 5 days: 28160 Euro/Catering: 7875 Euro/Meeting rooms 3 x 2,5 days: 4500 Euro/Staff PC 5 days: 2111,35 Euro/Staff PO 3 days: 1013,55 Euro/Staff D 3 days: 1591,17 Euro/Staff ADO 10 days: 3353,00 Euro/Staff PL 3 days: 1053.33 Euro/Staff MCO 2 days: 670,76 Euro/Staff AdO1 10 days: 2548,10 Euro for a total of 66956,26 Euro Staff PC 4 days: 1689,08/Staff PO 4 days: 1351,40 Euro/Staff Euro for a total of 3040,48 Euro Staff PC 2 days: 1060,78 euro/Staff PO 3 days:1013,55 Euro/FO 15 days:5266,65 Euro for a total of 7547,01 Euro |
| Strategic Objective 1.1: EAPN will work to ensure that the Europe 2020 strategy, the Platform…(see above), and Specific Objectives 1 and 4. | Monitoring Europe 2020 and the Semester: CSRs. EAPN’s Members’ assessments and proposals on CSRs are communicated in a timely and useful way to the European Commission. Monitor Europe 2020 and the Semester: National developments/NRPs. EAPN’s member’s assessment of delivery on poverty and participation in the NRPs is timely and effective. Findings are taken up in the Annual Growth Survey. | Synthesis report with country fiche annex providing an assessment of 2015 CSRs and their implementation, with proposals for amendments to CSRs with evidence and explanations based on members’ national inputs (see next section). Report on the Semester, drawing on members’ inputs related specifically to the NRPs/CSRs Key Messages to AGS. Will also be presented in Policy conference in October | Adapting template fiche and sending out. Getting responses from members. Discussion of draft responses in EUISG meeting. Analysis of response and development of synthesis. Drafting of Report. Circulation of Draft for comments. Finalised Report. Drafting/agreement of Questionnaire. National Exchange and consultation with members in the EUISG. Input from national members. Drafting of report. Final report and Dissemination Drafting of Messages. Finalisation and dissemination. Letter to Institutions Presentation in policy conference | (Dec 2015) January 2016 February 2016 February 2016 February 2016 Feb/March 2016 April-May 2016 June 2016 June 2016 July 2016 September - October 2016 July 2016 September 2016 October 2016 October 2016 | Staff PC 7 days: 2955,89/staff PO 7 days: 2364,95staff D 1 day: 530,39 for a total of 3908,72 Euro Staff PC 8 days: 3378,16/staff PO 8 days: 2702,80/staff D: 2 days: 1060,78 for a total of 7141,74 Euro Staff PC 4 days: 1689,08/ staff PO 4 days: 1351,4/ reports 4000,00 a total of 7040,48Euro |
| Strategic Objective 1.1. Specific Objective 1: Defend the poverty target and EAPN proposals for the Mid-Term Review of Europe 2020 in the Semester, monitor trends on poverty and get new EU commitments to reduce poverty through an integrated antipoverty strategy based on integrated Active Inclusion and Social Investment in quality jobs, services and social protection | EAPN proposals on the Mid-Term Review are taken on board in related EU documents. EAPN Members actively engage in dissemination and follow-up at national level. EAPN Analysis and Messages are debated with EU decision-makers and stakeholders | EAPN Response to Mid-Term Review Communication with Key Messages. (depending on date of adoption) Briefing paper on outcomes of Mid-Term Review and action that members can take. EAPN Policy conference [Outputs will include agendas/minutes, and also presentations and evaluations.] | Draft Messages Discussion of draft with members in the EUISG Finalised document sent to decision-makers disseminated Draft Briefing. Consultation with the EUISG. Final Briefing with dissemination also at national level. Preparing the Policy Conference – draft programme and logistics. Consultation with EUISG and EXCO. Finalisation of conference preparations. Delivery of conference. Report and evaluation. | Jan/Feb 2016 Feb 2016 Feb/March 2016 February 2016 Feb 2016 March/April April April- June 2016 June 2016 July-October 2016 October 2016 November | Staff PC 2 days: 844,54/ see EUISG 0,00/ staff PO 2 days: 844,54/ staff D 2 days: 1060,78 a total of 1905,32 Euro Staff PC 3days: 1266,81/ staff PO 3 days: 1013,55 a total of 2280,36 Euro See EUISG 0,00 Staff D 2 days: 1060,78/ staff PC 2 days: 844,54/PO 1 days: 337,85 for a total of 2243,17 Euro Catering: 50 persons x 1 day: 1000 /Staff PC 3 days: 1266,81/ staff D4 days: 2121,56/ staff AdO: 6 days: 2011,8/ staff FO 2 days: 702,22/ staff PO 3 days: 1013,55 / staff MCO 2 days: 670,76/ staff AdO: 2 days: 509,62/ staff Popf4 day: 1723,28/ a total of 11019,60 Euro Staff D 1 day: 530,39/ staff PC 1 day: 422,27/ staff PO 1 day: 337,85 a total of 1290,51 Euro See GA 0,00 Staff D 1 day: 530,39/ staff PO 2 day: 675,70/ staff PC 1 day: 422,27 a total of 1628,36 Euro |
| Strategic Objective 1.1 Specific Objective 1 and 4. | EAPN and Members actively monitor and engage with the implementation of key social policy areas related to the SIP - investing in children, homelessness and active inclusion. | 2 Policy Updates Engagement in Investing in Children Alliance Meetings Dissemination and discussion of activities, particularly at national level Follow up on Active Inclusion and implementation including follow up to EMIN and Reference Budget project findings. | Preparation Discussion in EUISG meetings. Participation in EU level regular meetings. Regular follow up Exchanges during EUISG meetings. Exchange in EUISG meetings. | January, May February, October 6 times a year All year All year All year | Staff PC 3 days: 1266,81/ staff D 1.5 days: 795,59/ staff PO 3 days: 1013,55 a total of 3075,95 Euro Staff PC 2 days: 844,54 Euro Staff PC 7 days: 2955,89/ staff D: 4.5 days: 2386,76 a total of 5342,65 Euro Staff: D: 2 days 1060,78 Euro, POPF: 6 days 2584,92 Euro; PC: 3 1266,81 euro for a total of 4912,51 Euro |
| Strategic Objective 1.1.: EAPN will work to ensure that the Europe 2020 strategy, the Platform (…..see above); Specific Objective 1 and 4. | EAPN has more effective engagement in the revised Annual Convention and EU thematic meetings. EAPN engages actively in EU stakeholder dialogues | Participation in EU stakeholder meetings related to EPAP and EU networks Contribute to development of Annual Convention and thematic meetings Organize participation of members including people experiencing poverty in revised Annual Convention Participation in Stakeholder Dialogue on Roma Inclusion, including NGO coalition. Participation in Stakeholder Dialogue on Vulnerable Consumers Group | Participation in regular meetings Preparation of contributions to Commission for revised AC and thematic meetings Organise participation of members in revised AC and workshops and possible side events and actively engage in preparations. Evaluation with members. Feedback to the European Commission. Participation in regular meetings Information and follow up with EAPN members. Participation in regular meetings Information and follow up with relevant EAPN members. | All year All year Jan-Feb and during the rest of 2016 March April All year All year All year All year | Staff: D 5 days 2651,95 Euro; PC : 4 days 1689,08 Euro; POPF: 1 day 430,82 Euro; PO: 3 days 1013,95 Euro for a total of 5785,40; Staff: PC: 3 days 1266,81 Euro; PO: 2 days 675,70 Euro; MCO: 2 days 670,76 Euro for a total of 2613,27 Euro Staff D: 6 days: 3182,34/ staff PC :4 days: 1689,08/staff PO :4 days: 1351,04/ staff AdO 6 days: 2011,80 a total of 8234,62 Euro Staff POPF 5 days: 2154,10 Euro Staff PO 5 days: 1689,25 Euro/PC 5 days: 2111,35 Euro for a total of 3800,60 Euro Staff PO 5 days: 1689,25 Euro/PC 5 days: 2111,35 Euro for a total of 3800,60 Euro PO: 1 day; DO 1 day, |
| Strategic Objective 1.1 Specific Objective 3. Contribute to proposals to make Progress on EU social standards, specifically through an EU social protection floor, adequate minimum income and minimum/living wages. | EAPN contributes to making progress on EU social standards related to decent work and minimum wages. | Follow up on the delivery of the employment target and the European Employment Strategy – with a view to monitoring implementation as part of Semester Review Assessment report(above) Follow up to EAPN paper on Inclusive labour markets | Consultation with members as part of NRP review Discussion in EUISG Finalizing key messages. Finalization of paper on Inclusive labour market Dissemination to Decision-makers | June- September October July - September Jan-Feb 2016 March 2016 | Staff PC 2 days: 844,54/ staff PO 4 day: 1351,40 Euro 337,85/ staff MCO 3 days: 1006,14 a total of 3202,08 Euro Staff PC 1 day: 422,27 Euro Staff PC 1 day: 422,27/ staff D 2 days: 1060,78/s staff PO 1 day: 337,85 a total of 1820,90 Euro Staff PC 2 days: 844,54/ staff D 1 day: 530,39/ staff PO 2 days: 675,70 a total of 2050,63 Staff PC 2 days: 422,27/ staff D 1 day: 530,39/ staff PO 2 days: 675,70 a total of 2472,90 Euro |
|  | EAPN contributes to information/awareness-raising around trends affecting affordable access to key public services building on Mapping Exercise in 2015, as contribution to social floor discussions. EAPN contributes to debates on Commission’s proposals on EU Social Floor to progress social standards | 1 mapping report, follow-up on the Mapping Exercise of 2015. EAPN position/input to EU debate on Social Floor/Social Standards with particular focus on adequacy of minimum income/ social protection and minimum/living wage | Draft Mapping Report Discussion with members in EUISG Finalization of Mapping Report Dissemination Information and Discussion in EUISG Meeting Preparation of Draft Written exchange Finalization of Draft and dissemination Consultation with EUISG | Feb 2016 Feb 2016 March 2016 April 2016 Feb 2016 March 2016 March 2016 April/May 2016 June 2015 | Staff PC 1 day: 422,27/ staff D 1 day: 530,39/ staff POPF 1 day: 430,82/ staff PO 1 day: 337,85 a total of 1721,33 Euro Staff PC 1 day: 422,27/ staff D 1 day: 530,39/ staff POPF 1 day 430,82/ staff PO 1 day: 337,85 a total of 1721,33 Euro Staff PC 2 days: 844,54/ staff D 1 day: 530,39/ staff POPF 1 day 430,82/ staff PO 2 days: 675,7 a total of 2481,45 |
| Strategic Objective 1.1 Specific Objective 2. | EAPN provides input to the Mid-Term Review of the MAFF EAPN regularly inputs its findings/experience into the EU Stakeholder Dialogue | 1 Position Paper/ Written and oral inputs to the Stakeholder Dialogue | Draft Position Paper Final Position Paper Dissemination Preparation of inputs with EAPN representative and EAPN members working on SF through EUISG | March 2016 April 2016 May 2016 All year | Staff PC 4 days: 1689,08/Staff PO 4 days: 1351,40 Euro/Staff Euro for a total of 3040,48 Euro |
| TOTAL: | 173871,25 |
| Additional information, if needed: N/A Please indicate deviations from the 4-years Work Programme, if any: N/A |

Priority 2: Support stakeholders' involvement in the policy process: activities should in particular directly relate to the support of national member organisations in their involvement in the implementation of the main political EU-driven processes. In addition, EU-level networks should encourage cooperation with other civil society organisations and social partners' organisations at EU, national, regional and local levels.

| Priority 2 is delivered through EAPN’s Strategic Objectives 1.1 and 2.2: Strategic Objective 1.1: EAPN will work to ensure that the Europe 2020 strategy, the Platform against Poverty and the Social Inclusion strategy (Social OMC), the Employment Policy (European Employment Strategy) and Cohesion Policy (Structural Funds) deliver progress to: effectively mainstream social concerns, reduce poverty and inequality and ensure that public policies, programmes and intervention reach people living in poverty, including the most disadvantaged. Strategic Objective 2.2: EAPN will provide opportunities for mutual exchange at bilateral and multilateral levels between its members to ensure a transfer of knowledge, experience and learning on practices and policies in the fight against poverty, social exclusion and inequalities; And through Specific Objective 4: Europe 2020 and Cohesion Objectives for 2015. Defend the poverty target and EAPN proposals for the Mid-Term Review of Europe 2020 in the Semester, monitor trends on poverty and get new EU commitments to reduce poverty through an integrated antipoverty strategy based on integrated Active Inclusion and Social Investment in quality jobs, services and social protection. Work to ensure that the minimum 20% of the ESF ear-marked for antipoverty is implemented, and support greater NGO engagement in the monitoring committees and in delivery; input to the Review of the Multi-Annual Framework to ensure better budgets for poverty. Contribute to proposals to make Progress on EU social standards, specifically through proposals for an EU social protection floor, adequate minimum income and minimum wages. Build capacity and achieve more meaningful and impactful engagement of stakeholders in Europe 2020/ and the European Semester and other policy processes at EU and national level. |
| --- |
| STRATEGIC OBJECTIVES in order to meet PRIORITY 2 | OUTCOMES | OUTPUTS (please quantify) | ACTIVITIES | TIMEFRAME PER ACTIVITY (mm/yy) | RESSOURCES AND PROVISIONAL BUDGET PER ACTIVITY (detailed breakdown) |
| Strategic Objective 1.1: EAPN will work to ensure that the Europe 2020 strategy, the Platform (…..see above); Strategic Objective 2.2.: EAPN will provide opportunities for mutual exchange at bilateral and multilateral levels between its members to ensure a transfer of knowledge, experience and learning on practices in the fight against poverty, and Specific Objective 4: See above | Achieve more effective engagement with increased impact by members in the Europe 2020 process. Strengthen capacity of members to engage in and build alliances more effectively around the Europe 2020 process. Better quality engagement in NRP and Semester process. More impact of policy proposals. EAPN engages in effective broad alliances to have better impact | EU capacity building workshop session as part of EUISG meeting. Report on capacity building as part of EUISG minutes Financial support (see additional information) will be given to national networks to support their work on the Europe 2020 Strategy and for national activities to feed into the European work of EAPN 1 Tool Kit on stakeholder engagement including section on social watch/poverty watch Support to members to develop national monitoring reports/social or poverty watch to support their input to NRPs and CSRs Engagement in the Semester Alliance, contribution to information and advocacy activities and support to national alliances | Preparation/organization of capacity building Delivery Evaluation Report and follow up Preparation of terms of reference Prepare and Sign contracts Initial funding Review outcomes with EUISG Revise Tool Kit draft Exchange in EUISG capacity building Finalize and Disseminate EUISG exchange review of stakeholder engagement in Semester as feed into NRP report and CSR(see above) Advice to members as part of capacity building above Collection and Dissemination of Member’s reports on-line and to EU institutions as relevant Participation in meetings of Semester Alliance Contribution to joint work including feedback on NRPs and CSRs and inputs to the Commission, Council and Parliament Information and mutual exchange on developments with national alliances. | January-February February March January February March April-December October January-February February March All year: Feb, October EUISG Feb 2015 All year All year All year All year | See EUISG 0,00 See EUISG 0,00 Staff PC 4 days: 1689,08/ staff / staff PO 4 days: 1351,40 / staff D 2 days/ 1060,78 a total of 4101,26 Euro External experts Euro Staff PC 4 days: 1689,08/ staff D 3 days: 1591,17/ staff FO 3 days: 1051,26/ staff POPF 3 Days 1292,46 / staff PO 3 days: 1013,55/ staff ADO 3 days: 1005,90 a total of 7645,49 Euro staff D 3 days: 1591,17/ staff PC 1 day: 422,27/ staff FO 5 days: 1755,55 / staff PO 1 day: 337,85 a total of 4106,84 Euro Staff PC 6 days: 2533,62/ staff D 5 days: 2651,95/ staff FO 20 days: 7008,40/ staff PO 6 days: 2027,10 a total of 14234,87 Euro 0,00 - EUISG Staff PC 1 day: 422,27/ staff PO 1 day: 337,85/ staff MCO 1 day: 335,38/ staff D 1 day: 530,39 a total of 1625,89 Euro Staff PC 1 day: 422,27/ staff PO 2 day: 675,7 / staff MCO 1 day: 335,38/ staff D 1 day: 530,39 a total of 1963,74 Euro Staff PC 2 days: 844,54/ staff PO 2 days: 675,7 / staff MCO 1 day: 335,38/ staff D 2 days: 1060,78 a total of 2916,4 Euro Staff PC 2 days: 844,54/ staff AF 1 day: 337,85/ staff NE 1 day: 335,38/ staff D 2 days: 1060,78 a total of 2578,55 Euro Staff PO 1 day: 337,85/ staff MCO 1 day: 335,38/ staff ADO 1 day: 254,81 a total of 928,04 Euro See EUISG 0,00 Staff PC 3.5 days: 1477,95/ / work on EU 2020 – 31 networks: 46500 81 a total of 47977,95 Euro |
| AY | Increased engagement of Members in Partnership Agreements and in delivery of Structural Funds projects building on the work in 2015 | Guidelines for Members on promoting grass-root projects building on Task Force work | Draft Guidelines disseminated for comments Final Guidelines Information and Capacity building session in EUISG Report in minutes | Feb-March May October December | See EXCO 0,00 See EXCO 0,00 Staff D: 3 days: 1591,17/ staff / staff PO: 2 days: 675,70/ staff PC: 1 day: 422,27/ staff POPF: 2 days: 861,64 / staff MCO: 3 day: 1006,14 a total of 4556,92 Euro |
|  |  |  | TOTAL: | 92635,95 |
| Additional information, if needed : Regarding the funding for the 31 national networks to work on Europe 2020 at national level: In 2015, EAPN launched pilot actions with a view to give additional support to national networks to raise awareness on Europe 2020. Funding was increased for a selected number of national networks to do the job, which is ongoing. While the pilot actions of 2015 appear successful in the pilot countries, EAPN networks in other countries received less and thus could only do a minimum of work on EU 2020. Though an evaluation is pending, the preliminary assessment is that – due to the cuts in the core budget – much less money is available for work on Europe 2020 and all national networks need and want to work on EU 2020. If there had been more money available for that work, the pilot actions could have been continued. Please indicate deviations from the 4-years Work Programme, if any : N/A |

| Priority 3: Strengthen the capacity of EU-level NGO networks and their national members, to support implementation of EU priorities as indicated under point III (Policy Context) including their knowledge of relevant EU matters. |
| --- |
| Priority 3 is delivered through EAPN’s Strategic Objectives 2.1, 2.2, 2.3, 3.1, 3.2, 3.3: Objective 2.1: EAPN will seek in a transparent fashion to actively engage the expertise of its members in its structures and working methods. Objective 2.2: EAPN will provide opportunities for mutual exchange at bilateral and multilateral levels between its members to ensure a transfer of knowledge, experience and learning on practices and policies in the fight against poverty, social exclusion and inequalities. Objective 2.3: EAPN will provide opportunities for capacity building for its members. Objective 3.1: EAPN will promote and strengthen the participation of people experiencing poverty within its internal workings. Objective 3.2: EAPN will encourage and strengthen the self-organisation of people experiencing poverty and social exclusion and/or their inclusion in anti-poverty NGOs. Objective 3.3: EAPN will, with the engagement of people experiencing poverty, seek out and promote good practices in participatory policy making and seek to demonstrate to people living in poverty the added value and impact of their contribution. |
| STRATEGIC OBJECTIVES in order to meet PRIORITY 3 | OUTCOMES | OUTPUTS (please quantify) | ACTIVITIES | TIMEFRAME PER ACTIVITY (mm/yy) | RESSOURCES AND PROVISIONAL BUDGET PER ACTIVITY (detailed breakdown) |
| Strategic Objectives 2.1: EAPN will seek in a transparent fashion to actively engage the expertise of its members in its structures and working methods, and | Increase the effectiveness of EAPN’s statutory bodies. Implement the results of an independent evaluation. Strengthen the culture of evaluation, self-assessment and growth among EAPN and its members. Improve knowledge about European policies and foster exchange of good practice. | Fulfilling the statutory duties and the proper functioning of EAPN. Approval/owner-ship of EAPN’s policy papers EAPN evaluation and new Strategic Plan presented at the EAPN General Assembly 2015. Approval of other statutory business including work programme 2017 as well as evaluation of work. | 3 meetings of the EAPN Bureau (additional meetings by Skype). 2 Meetings of the EAPN Executive Committee (36 representatives plus secretariat members/2.5 days for each meeting. One meeting organized in conjunction with the Policy Conference and the EU Inclusion Strategies Group. Meeting of the General Assembly of EAPN Preparation and follow-up of the GA 3 Meetings of the European Organisations members of EAPN | March, June, October March and October June May and July-August March, June, October | Travels 24 members: 5280 /subsistence 24 x 2 days: 6480 / staff D 15 days: 7955,85/ staff PC ½ day: 211,14/ staff FO 10 days: 3511,10 / staff ADO 6 days: 2011,80/ staff MCO 2 days: 670,76/ staff POPF 3 day: 1292,46 a total of 27413,11 Euro Travels 64 members: 14080 / subsistence 32 persons x 8 days: 28160 / catering 35 persons x 5 days: 7875 / / external experts: 1600,00/ meeting rooms 2 x 2,5 days:4500 / staff D 17 days: 9016,63 staff PC 4 days: 1689,08/ staff PO 4 days: 1351,40/ staff ADO 10 days: 3353,00 staff POPF 6 days: 2584,92 staff FO 15 days: 5266,65/ staff MCO 6 days: 2012,28 / staff ADO 6 days: 1528,86 / staff a total of 83017,82 Euro Travel 40 persons: 8800 / subsistence 40 x 2 days: 8800 / subsistence EUIS subscription to networks + platforms: 4000,00/ catering 43 x 1 days: 1935 / interpretation: 2850 / INT equipment: 1800,00/ meeting rooms: 500 / audits: 4000,00/ staff audits-finalization accounts FO 40 days: 14044,40 expert accountant: 5000,00/ expertise members 2000,00/ staff D 8 days: 4243,12/ staff PC 2 days: 844,54/ staff ADO 6 days: 2011,80/ staff FO 10 days: 3511,10 / staff MCO 2 days: 670,76/ staff POPF 8 days: 3446,56 / staff RL 2 days: 509,62/ Staff / staff AF 2 days: 675,70 a total of 69642,60 Euro |
| Strategic Objectives 2.2: EAPN will provide opportunities for mutual exchange…(see above); 3.1: EAPN will promote and strengthen the participation...(see above) and 3.3: EAPN will, with the engagement of people experiencing poverty, seek out and promote good practices in participatory policy making and seek to demonstrate to people living in poverty the added value and impact of their contribution. | Strengthening the governance of members, in particular new ones. Contacts with relevant persons in other European countries. Improve communication with new network in Slovenia. | The EXCO’s Membership Development Group plan a training and capacity building agenda for 2016 and provide support visits to 1 networks (agenda and notes from the meetings). 1 capacity building seminars on anti-poverty work, policy-making and participation of people experiencing poverty (reports and supporting documents). One National Networks undergo Membership Assessment and Support (MASS) (reports from meetings). Contact established with new networks. Support provided to new members. [The work of the EU Inclusion Strategies Group and the relevant policy task forces also contribute to these objectives.] | 2 Meetings of Membership Development Group (7 people – a third meeting will be organised on Skype). Visiting 1 network. Delivery of 1 capacity building seminar (3 days meeting with 30 participants). Delivery and evaluation. Follow-up. Support meetings to 1 National Networks undergoing MASS (one follow-up from 2014 and 2 new National Networks) and other travels for representing EAPN at European meetings. Raising visibility of Europe 2020 strategy by speaking in events of members and partners with a view to bringing the EU perspectives on poverty and social exclusion. | April, October Visits in 2nd quarter to be fixed with the Network involved. May May to November April to December 2nd and 3rd quarters Throughout the year, upon invitation Throughout the year | Travel 6 x 2 meetings: 2640 subsistence 6x 4 days: 2640 / catering 7 x 1 days: 630/ staff D 5 days: 2651,95/ staff / staff FO 3 days: 1053,33 staff ADO 5 days: 1676,50 / staff NE 2 days: 670,76 / staff PC 3 days: 1266,81/ staff PO 3 days: 1013,55 for a total of 14242,90 Euro Travels 30 persons: 6600 / subsistence 35 30 persons x 3 days: 13200 / catering 35 persons x 3 days: 4725 / meeting rooms 2x2 days: 1200 / external experts: 1600,00/ staff POPF 8 days: 3446,56 staff / staff D 5 days: 2651,95/ staff ADO 8 days: 2682,40/ staff FO 2 days: 702,22 staff MCO 3 days: 1006,14 staff ADO 3 days: 764,43 / staff PC 3 days: 1266,81/ staff PO 3 days: 1013,55 a total of 40859,06 Euro Staff ADO 3 days: 1005,90/ staff D 2 days: 1060,78 POPF 3 days: 1292,46 Euro a total of 3359,14 Euro Staff f FO 4 days: 1404,44 / staff D 1 day: 530.39/ POPF 4 days: 1723,28 Euroa total of 3658,11 Euro Travels 34 persons: 7480 / subsistence 34 persons x 2 days: 7480 / catering 34 persons x 1.5 days: 2295 / meeting rooms 6 days: 1800,00/ staff PC 7 days: 2955,89/ staff D 6 days: 3182,34/ staff PO 7 days: 2364,95/ staff POPF2 days: 861,64/ Staff for a total of 28419,82 Euro. |
| Strategic Objectives 2.2: EAPN will provide opportunities for mutual exchange…(see above), and 2.3: EAPN will provide opportunities for capacity building for its members. | EAPN Communication and Information Strategy designed and implemented with active involvement of members Support transfer of good practice. Ensure the continuance of high quality and timely communication and information work. | Information dissemination via EAPN web-site/Mailchimp 2 Policy Updates ( see page 8) 2 EAPN briefing papers At least 4 EAPN reports and position papers. Timely EAPN letters and EAPN templates. EAPN Press Releases responding around Council meetings and important events. | EAPN external website updated – used as a reference website on poverty and social exclusion in the EU. Maintain blogs dedicated to main policy Areas and on-going communication capacity building work. Publication of press releases and accompanying papers EAPN position papers/letters/messages. Maintain and develop contacts with media | Throughout the year Throughout the year Throughout the year Throughout the year | Publications: 3000,00/ staff MCO 18 days: 6036,84/ staff ADO 20 days: 5096,20 / staff D 2 days: 1060,78/ staff ADO 2 days: 670,60 a total of 15864,42 Euro Publications: 2000 / staff MCO 8 days: 2683,04/ staff ADO 20 days: 5096,20 / staff D 2 days: 1060,78/ staff ADO 670,60 a total of 11510,62 Euro Publications: 3000 / mailings: 1000,00/ staff MCO 18 days: 6036,84/ staff ADO 46 days: 11721,26 / staff D 5 days: 2651,95/ staff ADO 2 days: 670,60 a total of 25080,65 Euro Publications: 2000,0/staff MCO 20 days: 6707,60/ staff ADO 24 days: 6115,44 / staff D 1 day: 530,39/ staff ADO 2 days: 670,60 a total of 16024,03 Euro Staff MCO 6 days: 2012,28/ staff ADO 4 days: 1019,24 / staff D 1 day: 530,39 a total of 3561,91 Euro Staff MCO 6 days: 2012,28/ staff ADO 8 days: 2038,48 / staff D 1 day 530,39 a total of 4581,15 Euro |
|  |  | Updated EAPN website and blogs. Activities on blogs. Social media presence. Online photo albums. | Regular update of an active Intranet for EAPN membership. Voices from people experiencing poverty made visible on the website. Dissemination of publications and briefing papers via email, web, blogs, social media - targeting EU institutions, media, other stakeholders. General publications/awareness raising. General publications. Upkeep online photo albums. | Throughout the year Throughout the year Throughout the year Throughout the year Throughout the year Throughout the year | Maintenance: 3000 / staff MCO14 days: 4695,32/ staff ADO 6 Days: 1528,86 / staff D 3 days: 1591,17 a total of 10815,35 Euro Maintenance 1000,00/ staff MCO 11 days: 3689,18 / staff ADO 6 days: 1528,86 / staff D 3 days: 1591,17 a total of 7809,21 Euro Documents by 31 national networks: 37800,00 Euro |
| Strategic Objective 2.2: EAPN will provide opportunities for mutual exchange…(see above). | Strengthening cooperation between EAPN members and other partners and contributing to the financial stability of EAPN and its members. Providing opportunities for mutual exchange between members to ensure transfer of knowledge, experience and learning on practices and policies in the fight against poverty and social exclusion. | Information on funding opportunities identified and disseminated to members. Project applications and results from projects disseminated. Developing the ability of EAPN to engage with projects and identifying the most suitable structure for EAPN and its members to be better able to engage in project work. | Identifying opportunities for members and disseminating information on projects related to EAPN’s strategic goals. Project applications submitted by EAPN in partnership with members and other stakeholders. | Throughout the year On-going and when funding calls are issued | Staff POPF 25 days: 10770,50 / staff / staff D 1 day: 530,39 a total of 11300,89 Euro Staff POPF 18 days: 7754,76 / staff / staff D 1 day: 530,39 a total of 8285,15 Euro |
| Strategic Objective 2.3: EAPN will provide opportunities for capacity building for its members. | Implementation of the EAPN Fund Raising Strategy. ‘Donor Strategy for EAPN. Ensuring the future financial sustainability of EAPN and its members. Management of EAPN Fund in KBF Foundation. | EAPN project applications (see above) EAPN inputs in support of public funding for Anti-Poverty NGOs. Contacts with Foundations. Possible Fund raising events and individual donor programme. Minutes of Fund Management Committee Grants to EAPN members on participation and stronger anti-poverty networks. | Developing and Implementing EAPN Fund Raising Strategy: Building and advocating the case for public support for anti-poverty organisation Developing an individual donor programme for EAPN Identifying potential fundraising events – Developing EAPN’s project activities, including applications for projects (see above) Building relations with Foundations and potential large donors. Supporting the management of the EAPN Fund in the KBF Foundation and liaison with the EAPN fund management Committee. Follow up re grants from the EAPN Fund | On going | Staff D 1 day: 530,39/POPF 2 days: 530,39 for a total of 1392,03 Euro POPF 20 days: 8616,40 |
|  |  |  | TOTAL: | 433254,37 |
| Additional information, if needed: Goal 3 of EAPN Strategic Plan is a transversal goal related to fostering direct participation of people living in poverty and social exclusion in EAPN’s internal and external workings. It is addressed throughout, but especially under Priority 3 and Priority 4. The EAPN Executive has decided to set up, from among themselves, a permanent group dealing with membership development, replacing short-term task forces and ensuring continuous support to EAPN National Networks along four pillars of strong anti-poverty network: National and EU policy-making processes around Europe 2020 and on sustainable societal models, participation of people experiencing poverty, development and growth of Networks and good governance and strong internal democracy. This group will take the results of the Task Forces on Membership Assessment and Support and the one on Training and Capacity Building and will define the priorities in the training, capacity building, member support, participation and enlargement areas. Considering the challenges of engaging with the Europe 2020 Strategy nationally, EAPN Executive has decided to implement two capacity building meetings for members in 2015, in addition to the mainstreamed capacity building in all the policy work of the network. One of them will be an induction seminar on understanding EU, Europe 2020 and the European anti-poverty policies and engaging with them. The other one will be defined by the Membership Development Group and will be targeting people with more advanced knowledge of EAPN European engagements. Please indicate deviations from the 4-years Work Programme, if any: N/A |

| Priority 4: Providing data and strong evidence base on policy developments and trends as well as collection of relevant information about citizens' concerns and good practices (using the knowledge bank) in the social policy field in the Member States, so as to contribute to better policy making. |
| --- |
| Priority 4 is delivered through EAPN’s Strategic Objectives 1.1, 2.2, 3.1, 3.2, 3.3: Objective 1:1: EAPN will work to ensure that the Europe 2020 strategy, the Platform against Poverty and the Social Inclusion strategy (Social OMC), the Employment Policy (European Employment Strategy) and Cohesion Policy (Structural Funds) deliver progress to: effectively mainstream social concerns, reduce poverty and inequality and ensure that public policies, programmes and intervention reach people living in poverty, including the most disadvantaged. Objective 2:2: EAPN will provide opportunities for mutual exchange at bilateral and multilateral levels between its members to ensure a transfer of knowledge, experience and learning on practices and policies in the fight against poverty, social exclusion and inequalities. Objective 3.1: EAPN will promote and strengthen the participation of people experiencing poverty within its internal workings. Objective 3.2: EAPN will encourage and strengthen the self-organisation of people experiencing poverty and social exclusion and/or their inclusion in anti-poverty NGOs. Objective 3.3: EAPN will, with the engagement of people experiencing poverty, seek out and promote good practices in participatory policy making and seek to demonstrate to people living in poverty the added value and impact of their contribution. And through Specific Objectives : Europe 2020 and Cohesion Objectives for 2016. Defend the poverty target and EAPN proposals for the Mid-Term Review of Europe 2020 in the Semester, monitor trends on poverty and get new EU commitments to reduce poverty through an integrated antipoverty strategy based on integrated Active Inclusion and Social Investment in quality jobs, services and social protection. Work to ensure that the minimum 20% of the ESF ear-marked for antipoverty is implemented, and support greater NGO engagement in the monitoring committees and in delivery; input to the Review of the Multi-annual Framework to ensure better budgets for poverty. Contribute to proposals to make Progress on EU social standards, specifically through proposals for an EU social protection floor, adequate minimum income and minimum wages. Build capacity and achieve more meaningful and impactful engagement of stakeholders in Europe 2020/ and the European Semester and other policy processes at EU and national level. |
| STRATEGIC OBJECTIVES in order to meet PRIORITY 4 | OUTCOMES | OUTPUTS (please quantify) | ACTIVITIES | TIMEFRAME PER ACTIVITY (mm/yy) | RESSOURCES AND PROVISIONAL BUDGET PER ACTIVITY (detailed breakdown) |
| Strategic Objectives 1.1: EAPN will work to ensure that the Europe 2020 strategy, the Platform (…..see above); 2.2: EAPN will provide opportunities for mutual exchange…(see above), and Specific Objectives 1-4. | Building better evidence of key trends, policy developments with examples of good practices in the area of poverty and social inclusion, building on national experience. All EAPN members will benefit from the findings/outputs of the TF, through mutual learning and share in the dissemination. | 2 Policy Task Forces of 6-8 people meeting 2 times in the year with production of agreed deliverables with timeline. The outputs will be agreed in Oct 2015 by EUISG. | Finalization of Scoping Note with TF host, confirming deliverables/timeline. Selection of TF members by EUISG Preparation/organization of meetings. Coordination of delivery of the main agreed outputs and dissemination Delivery of 2Task Force meetings for each TF (2) ie 4 TF meetings in total. Preparation of briefings on the basis of the work of the taskforces Finalization Exchange with EUISG on progress/findings Info processing Final meeting/Evaluation. Finalization of deliverables/dissemination | January February/March March April, September, November February - June September The 2 EUISG meetings June to November December | Staff PC 2 days: 844,54/ staff D 2 days: 1060,78 for a total of 1905,32 Euro Staff PC 6 days: 2533,62/ staff D 2 days 1060,78/ staff ADO 16 days, 5364,80/ staff FO 6 days: 2106,66 / staff PO 6 days: 2027,10/ staff MCO 6 days: 2012,28 a total of 15105,24 Euro Travels 24 persons/ 5280 / subsistence 6 persons x 6 days: 3960 / catering 6 persons x 6 days: 1620 / staff PC 6 days: 2533,62/ staff D 6 days: 3182,34/ staff PO 6 days: 2027,10/ staff ADO 14 days: 4694,20/ staff MCO 6 days: 2012,28/ external experts (6 days): 2400 a total of 27709,54 Euro Staff PC 6 days: 2533,62/ staff D 6 days: 3182,34/ staff PO 6 days: 2027,10/ staff ADO 10 days: 3353,00/ staff MCO 6 days: 2012,28/ staff FO 16 days: 5617,76 a total of 18726,10 Euro Staff PC 2 days: 844,54/ staff PO 2 days: 675,70/ staff D 2 days: 1060,78 a total of 2581,02 Euro Staff PC 2 days: 844,54/ staff PO 2 days: 675,70/ staff D 2 days: 1060,78 a total of 2581,02 Euro Staff PC 2 day: 844,54/staff PO 2 days: 675,70/ staff D 2 days: 1060,78 a total of 2581,02 Euro Staff PC 8 days: 3378,16/staff PO 8 days: 2702,80/ staff ADO 4 days: 1341,20 a total of 7422,16 Euro Staff PC 8 days: 3378,16/staff PO 8 days: 2702,80/ staff D 4 days 2121,56/ staff MCO 2 days: 670,76 a total of 8873,28 Euro Staff PC 7 days: 2955,89/ staff PO 6 days: 2027,10/ staff D 5 days: 2651,95/ staff MCO 2 days: 670,76 a total of 8305,70 Euro |
| Strategic Objectives 3.1: EAPN will promote and strengthen the participation…(see above), 3.2: EAPN will encourage and strengthen the self-organisation…(see above), and 3.3: EAPN will, with the engagement of people experiencing poverty, seek out …(see above). | Ensuring that the delegates (people experiencing poverty) have more ownership of and engagement in the PeP meetings. Working with partner institutions to prepare the meeting. Identifying facilitators and plan the methodology of the meeting. Evaluation and follow up on the main theme of the meeting. | National Coordinators meeting Guidance for national preparation for the EU Meetings of People Experiencing Poverty and for developing participation in EAPN. Report of the EU meeting of People Experiencing Poverty. Key messages from EU Meeting of People Experiencing Poverty and Social Exclusion. | 1 preparatory meeting of National Coordinators for the EU PEP meeting and for developing participation in EAPN. Meetings with facilitators for workshops. Preparatory meetings with partner institutions. EU Meeting of People Experiencing Poverty and Social Exclusion. Report of the Meeting. Key messages from the Meeting. Voices from people experiencing poverty taken up on EAPN website and blog, and in relevant communication work. Dissemination of report and key messages. | February March ongoing Date to be fixed in partnership with institutions After the meeting After the meeting After the meeting 3rd Quarter | Travel 30 persons: 6600,00/ subsistence 30persons x 2 days: 6600,00/ catering 35 persons x 1 day: 1575,00/ meeting room 1 day: 300,00/ staff POPF 5 days: 2154,10/ staff ADO 3 days: 1005,90/ staff FO 7 days: 2457,77 / staff D 5 days: 2651,95 a total of 23344,72 Euro Work by the national networks on Pep: 279000 / staff FO 25 days: 8777,75 staff D 5 days: 2651,95 a total of 293629,70 Euro Staff POPF 4 days: 1723,28 Staff POPF 4 days: 1723,28 a total of 3446,56 Euro staff POPF 8 days: 3446,56 / staff D 2 days: 1060,78/ staff MCO 3 days: 1006,14 a total of 5513,48 Euro staff MCO 1 day: 335,38 Euro staff MCO 3 days: 1006,14/ staff ADO 4 days: 1019,24 a total of 2025,38 Euro |
| Strategic Objective 3.1: EAPN will continue to increase the direct participation of people experiencing poverty within its internal workings, and Strategic Objective 3.2: EAPN will work to ensure strengthened self-organization of people experiencing poverty and social exclusion and/or their inclusion.. | Activists with direct experience of poverty participate in EAPN statutory and working groups and key visibility events. | Lists of participants and input into key EAPN documents from activists with direct experience of poverty. | Work with members to promote the use of the Guidance on Civil Dialogue on Europe 2020 in National and EU contexts. Involve the expertise of activists with direct experience of poverty and social exclusion in most of our structures. Involve activists with direct experience of poverty in the Annual Convention. Build on the Annual EU Meeting of People Experiencing Poverty. | January to June Throughout the year June June to December |  |
| Strategic Objectives 1.1 -3.2 | Capacity Building for EAPN Secretariat Personal Skills/Rent Depreciation Equipment EAPN Admin Costs EAPN: Electricity/Telephone/Internet/Office Supplies/Photocopies/Insurances/etc Support from and training opportunities for stagiaires | Improved support for delivery of project Ensure the proper delivery of the project 3 Stagiaires per year | Staff Development Days Working with Erasmus and/or members/implement training programme | All Year Jan-Dec Jan-Dec Jan-Dec Jan-Dec | All Staff 1080 Euro 2200,00 Euro 6600,00 Euro 111191,03 Euro 1500 Euro |
| Additional information, if needed : N/A Please indicate deviations from the 4-years Work Programme, if any: N/A |
|  |  |  | TOTAL: | 546656,65 |

To be filled by all applicants

2. Risk Management

No more than two paragraphs presenting the internal process in place designed to identify and assess future risks that could impair the performance of the Partner Organisation and the mitigating actions to respond to such risks.

In 2013, the Director of EAPN examined the exposure to risk in the past and whether some of the risks had materialised and with what consequences (i.e. employees leaving unexpectedly; expected funding did not come through or too late). She also looked at what actions had been taken and the likelihood of that happening again.  On the basis of her assessment, she identified possible risks: loss of income; shortage of cash, new decision-makers in relevant public bodies, membership issues, etc.  These were then used to serve as the basis for examining potential risk factors.  The Director reported these factors to the Bureau and the Executive Committee. The Bureau is mandated to deal with such emergencies, but needs to report them to the Executive Committee. With a new Executive and Bureau in place since July 2015, the Director will undertake to develop a swot analysis and report the Bureau and Executive in October 2015 in order to minimize risks in 2016 and develop adequate responses to perceived risks.

3. Monitoring system

Please describe your monitoring system (taking into account also the Performance Measurement Plan as described in the 4-year work programme).

Quantitative monitoring:

All meetings, conferences and engagements that EAPN participates in are recorded and put into a database. So are press articles, web activity, distribution of printed materials, participation of members and Secretariat in EAPN’s meetings, participation of members and Secretariat in EU level events, and participation at our public events.  These statistics are compared to the statistics of previous years. If there are great deviations, the reasons for that will be analysed and if needed corrective actions will be taken. The results of evaluation are also monitored carefully.

Qualitative monitoring:

EAPN members are required to submit yearly reports as to their activities.  These national reports are evaluated taken the performance measures into account.  Members also receive questionnaires relating to their engagements at national level.  All EAPN meetings are evaluated by the participants as to their effectiveness, meeting the specific objectives.  The same holds true for statutory meetings or meetings of the EU Inclusion Strategies Group which provide essential feedback on performance.

EAPN held Strategic Congress in 2015 to develop a new strategic plan for 2016-2018.  The new strategic plan will be accompanied by a set out expected outcome which will have concrete qualitative and quantitative indicators allowing for a more structured monitoring.

All meetings are minuted and are also put into a database.

Regular meetings on performance with the secretariat as well as between the secretariat and the Bureau of EAPN provide space for evaluation and reflection to redress performance. In all cases, the performance measures guides the system.

4. External evaluation

Please indicate how and when the external evaluation will be carried out, to which extent will use the results of the monitoring system put in place, and also how it will help to report on performance.

EAPN has put in place an external evaluation process beginning with 2013, which aims to identify the way EAPN is implementing its Strategic Plan objectives and the priority areas to be taken up in the revised strategic plan 2016-2018. An external independent evaluator was hired to collect data internally, to assess the organisation’s performance measures as indicated in the Quadrennial Strategic Action Plan. The process began with desk research and analysis of all the evaluation and performance monitoring data available to EAPN from meetings, groups, external representation work. Furthermore, a questionnaire and interviews with members and representatives of statutory bodies and the secretariat were organized. The independent evaluator carried out an extensive external evaluation research through several interviews with decision-makers from EU institutions and from other stakeholders cooperating with EAPN. The Executive Committee of EAPN agreed on the final evaluation which then was the basis for the discussion of a new strategic plan. The new work programme for 2016 takes account of a findings of the external evaluation that more training and visibility is needed to promote Europe 2020.

# Footnotes

The Social Investment Package announced in particular the establishment of a knowledge bank to facilitate the exchange of good practice. The knowledge bank should allow experts, stakeholders and policy makers to define social policy challenges, to propose solutions and to discuss their strengths, weaknesses, limitations and transferability. The Commission will establish such a tool which should also be widely used by the EU-level networks supported under this call.