## TIMELINE
Timeline | [5 empty] | RL 26/02
Products in black
Events in blue |  | FEBRUARY |  | MARCH |  | APRIL |  | MAY |  | JUNE |  | JULY |  | AUGUST |  | SEPTEMBER |  | OCTOBER |  | NOVEMBER |  | DECEMBER
Comms actions in red | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| 3 |  | 3 | • Bureau meeting • Letter to the 10-03 EPSCO Council: sending and dissemination | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | EUISG | 3 |  | 3
Deliverables not yet on timeline | 4 |  | 4 | EU Elections' campaign LAUNCH (press breakfast briefing with MEPs, Press,Eos, BAPN) | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 | EUISG Annual Policy Seminar | 4 |  | 4
Learning Forum Report | 5 |  | 5 | • EAPN Flash | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
Campaign postcard | 6 |  | 6 | Press release on EPSCO Council (with AGS response) | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | EMIN European conference and Management Committee | 6
Update of the Poverty explainer | 7 | EUISG Meeting | 7 | • PR on AGS with EPSCO Letter • Final draft EAPN's CSR analysis sent to comms | 7 |  | 7 |  | 7 |  | 7 |  | 7 |  | 7 |  | 7 |  | 7 | EMIN European conference and Management Committee | 7
Youth inclusion mapping | 8 | EUISG Meeting | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8
Toolkit on ICTs | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  | 9
Migration & the crisis report TASK FORCE - publication either in early June (Integration Forum) or September, issue with launch event linked with policy makers | 10 |  | 10 | • Layout deadline for EAPN's CSR analysis | 10 | EMIN Management Committee | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10
Toolkit on decent work campaign TASK FORCE | 11 |  | 11 | • Letter to 18-03 General Affairs Council and 20-03 Spring Council | 11 |  | 11 |  | 11 |  | 11 |  | 11 |  | 11 | EMIN Peer Review and Management Meeting | 11 |  | 11 |  | 11
Policy Brief | 12 |  | 12 | • Task Force (3) Stakeholder Engagement • PR on + general dissemination of EAPN's CSR analysis | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 | EMIN Peer Review and Management Meeting | 12 |  | 12 |  | 12
| 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  | 13
NRP report | 14 | CSR Alliance Steering group | 14 | EXCO | 14 |  | 14 |  | 14 |  | 14 |  | 14 |  | 14 |  | 14 |  | 14 |  | 14
New EAPN leaflet | 15 |  | 15 | EXCO | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15
SFs handbook | 16 |  | 16 |  | 16 |  | 16 | EUISG Meeting | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  | 16
Leaflet on social inclusion & structural funds - highlighting interesting practices | 17 | • AGS Response - Specific diss. To SPC/EMCO and EPC • Water Campaign EP Hearing • EAPN Flash | 17 | • Press release on General Affairs and Spring Council • Dissemination of Alliance CSR Report at the hearing | 17 |  | 17 | EUISG Meeting | 17 |  | 17 |  | 17 |  | 17 |  | 17 |  | 17 |  | 17
Community-lead local development & SFs position paper (probably dropped) | 18 |  | 18 | EP EMIN event | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18
| 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  | 19
| 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 | Annual Convention | 20
| 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 | Annual Convention | 21
| 22 |  | 22 |  | 22 |  | 22 |  | 22 |  | 22 |  | 22 |  | 22 | PEP Meeting | 22 |  | 22 |  | 22
| 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 | PEP Meeting | 23 |  | 23 |  | 23
| 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 | PEP Meeting | 24 |  | 24 |  | 24
| 25 | EU Elections' campaign: meeting with Eos | 25 | Give a voice to citizens Toolkit - final draft sent to comms (?) | 25 |  | 25 |  | 25 |  | 25 |  | 25 |  | 25 |  | 25 |  | 25 |  | 25
| 26 | • FEAMD joint press release | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  | 26
| 27 |  | 27 |  | 27 |  | 27 | EXCO | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  | 27
| 28 | Task Force (2) Decent Work Task Force • CSR Report diss. to EC • Employment letter to Andor? | 28 |  | 28 |  | 28 | GA | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  | 28
|  |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 |  | 29
|  |  | 30 |  | 30 |  | 30 |  | 30 |  | 30 |  | 30 |  | 30 |  | 30 |  | 30 |  | 30
|  |  | 31 |  |  |  | 31 |  |  |  | 31 |  | 31 |  |  |  | 31 |  |  |  | 31