B7b. Work Planning 2019

Strategic Thinking

Timeline for Action on key team deliverables

staff and members in 2019

| Month | Strategic Thinking Actions |
| --- | --- |
|  | Staff (S) and Bureau (B) | Members |
| January |  |  |
| February | Participation / Dutch resolution paper (S) Draft the governance / structures paper (S/B). This paper needs to build on the ‘underpinning activity’ and the 4 priorities identified in the ‘theory of change’ Share Dutch resolution with whole network, offering feedback mechanisms (S) Monthly update (S/B) | Members |
| March | Prepare Ex Co meeting / Strategic Thinking discussions (S/B) Further develop governance / structures paper based on Bureau discussions (S/B) Monthly update (S/B) | Comm’on Group to look at Participation / Dutch resolution paper Bureau to look at Participation / Dutch resolution paper Bureau to develop governance / structures paper EUISG to provide input on participation / Dutch resolution paper |
| April | Compile PeP input into easy document, for discussion with PeP Coordinators in May (S) Incorporate changes / feedback to governance / structures paper (S) Prepare options for 5-6 areas of thematic focus for next 5 years, with justification (S/B) Monthly update (S/B) Sort contract for graphic facilitation (S) | Ex Co to discuss governance / structures paper |
| May | Support members to prepare resolutions (S/B) Prepare Ex Co / EUISG discussion (S/B) Build on research of Valentina to analyse potential income sources and opportunities, based on strategic plan (S/B) Revise governance / structures paper to take into account the 5-6 areas of thematic focus over next 5 years (S/B) Monthly update (S/B) | Bureau to discuss 5-6 areas of thematic focus, recommendations to Ex Co PeP Coordinators key discussion about Dutch paper as well as the key PeP input – how best this can fit in and be reflected Build on research of Valentina to analyse potential income sources and opportunities, based on strategic plan |
| June | Share papers with Ex Co / EUISG at least 2 weeks before the discussion (S) Monthly update (S/B) Draft final paper with Consultant (S) | Resolutions based on the Theory of Change to be prepared and shared Ex Co / EUISG discussion, focusing on governance / structures paper and potential resolutions |
| July | Prepare GA session – methodology etc (S/B) Monthly update (S/B) |  |
| August | Prepare GA session – methodology etc (S/B) Prepare the Staffing Review (S/B) Monthly update(S/B) |  |
| September | Circulate details of session at least 2 weeks before (S) Lead session (S/B) Write up notes of session (S) Share decisions with full network and partners, funders etc (S/B) Monthly update (S/B) Revise final paper following GA discussions, votes etc (S) | Read papers in advance, discuss with network Vote on resolutions at the General Assembly |
| October | Staffing review starts (B/S) Monthly update (S/B) | Start to discuss and implement changes |
| November | Staffing review (B/S) Monthly update (S/B) | Start to discuss and implement changes |
| December | Staffing review completed (B/S) Monthly update (S/B) | Start to discuss and implement changes |