Decisions and Action Points from August 2019 Bureau

Decisions

D1. If possible, we should have the General Assembly in Germany next year, to coincide with German Presidency of the EU Council.

Actions

| Action | Responsible | Deadline |
| --- | --- | --- |
| A1. Send any comments on the minutes to Leo | Bureau members | 20 August |
| A2. Take forward previous action point on planning Ex Co session looking at roles and responsibilities of different EAPN structures | Leo and Vera, then Magda and Biljana when they are back | End August |
| A3. Take forward the planning of a Stakeholder Analysis on our key issues | Eleni, Vera and Leo, then with Sian when she gets back | End August |
| A4. Send further comments on the draft document about 30th celebrations | All Bureau members | 20 August |
| A5. Discuss celebrations further and write into Work Programme | Leo and Eleni | End August |
| A6. Develop a timeline of actions throughout 2020 | Eleni, with Leo | End August |
| A7. Rework the documents for Ex Co and send to Bureau | Ian | 16 August |
| A8. Send comments on documents | Bureau members | 23 August |
| A9. Incorporate any Bureau comments into documents, incorporate an example (Family members, Eleni) | Ian | 26 August |
| A10. Send documents to Ex Co | Leo | 30 August |
| A11. Discuss the wellbeing and burnout policies, and the response from Rebecca, to plan next steps | Ian and Leo | Early September |
| A12. Send comments on draft agendas | Bureau members | 16 August |
| A13. Rework agendas | Leo | 23 August |
| A14. Work together to plan the Ex Co info sharing session | Leo, Vera, Magda, Membership Development Group | 30 August |
| A15. Work together to plan the Theory of Change discussion | Leo, Eleni, Noeleen | 30 August |
| A16. Reach out to EAPN Germany to check their willingness and capacity to organise the General Assembly meetings next year. | Leo | End October |
| A17. Work together to plan the Ex Co session on structures | Eleni and Leo | Early September |
| A18. Draft and send reminder email to Ex Co, EUISG, Comm’on, PeP NC, outlining the general rules for reimbursement, and these decisions. | Philippe to draft, Leo to check, Richard to send | End June |