## Interplay SR_FPA_SGA
FPA |  | SGA
ACTIVITY |  | WORK PACKAGE |  | ACTIVITY | STRATEGIC REVIEW - 4 PRIORITIES
|  |  |  | TASK | A. Policy Expertise | B. Strengthen the involvement of people experiencing poverty | C. Building public support and pressure for the eradication of poverty and an end to neoliberalism austerity politics | D. Advocate and campaign for social protection
Supporting and reinforcing EAPN’s capacity for Joint Planning and Delivery (WP1) | } | 1 | General Management and running of the organisation | Task 1.1 - Joint planning and delivery
Monitoring and evaluation of EAPN annual activities (WP1) |  |  |  | Task 1.2 - Monitoring and evaluation
Exploratory study on the usage of digital tools by people experiencing poverty (WP1) |  |  |  | Task 1.3 - Exploratory study on the usage of digital tools by people experimenting poverty
Research and collection of evidence based on the experience of poverty, quantitative data and analysis of anti-poverty policies, incorporating cross-cutting factors such as gender, disability, ethnic-cultural diversity and sexual orientation (WP2) | } | 2 | Multidimensional Poverty and Cross-cutting Factors | Task 2.1 - Comprehensive analysis of the reality of poverty and inequalities in the EU | Monitoring the situation of poverty throughout Europe | We will aim to base our policy work on participatory research with people experiencing poverty. | Developing challenging frames and narratives, and alternative social and economic political options. | Advocate and campaign for social protection systems
Task 2.2 - Dissemination to EU institutions of the information, knowledge and policy recommendations on the challenges faced by vulnerable groups
Awareness raising of EU and national authorities about the reality of poverty in Member States (WP2) |  |  |  | Task 2.3 - Communication action to relevant EU institutions of the key results and recommendations of the 2022 Poverty watch
Task 2.4 - Advocacy activities, using the 2022 EU poverty watch
Comparative research on the implementation of the European Pillar of Social Rights at the national level, including the and supervision of the specific commitments of the Member States (WP3) | } | 3 | EPSR Implementation | Task 3.1 - Follow up and engagement action on the implementation of the EPSR AP at national and local level | Pushing for the implementation of political commitments like the Social Pillar and the SDGs, via policy work at the national and European level | We will aim to base our policy work on participatory research with people experiencing poverty. | Developing challenging frames and narratives, and alternative social and economic political options. | Advocate and campaign for social protection systems
Evidence-based research on the implementation of key policy contents of the European Pillar of Social Rights (WP3) |  |  |  | Task 3.2 - Advocacy actions, supported by the ESPR report
Task 3.3 - Assessment of the 2030 national poverty goal
Comparative research and capacity building of national networks for governance on the European Semester, European funds and Recovery and Resilience Plans (WP4) | } | 4 | European Semester, Structural Funds and Recovery & Resilience Plans | Task 4.1 - Comparative research and capacity building on the governance of the EU Semester, EU Funds and the Recovery and Resilience Plans | Developing policy expertise on an agreed, limited number of themes within key areas, notably: a) A multidimensional approach to poverty, social exclusion and inequality, b) Access to social and economic rights, c) Access to quality services, d) Cross-cutting priorities, notably Environmental, technological and demographic challenges, and gender | We will aim to base our policy work on participatory research with people experiencing poverty. | Developing challenging frames and narratives, and alternative social and economic political options. | Advocate and campaign for social protection systems
Awareness raising of EU authorities and decision-makers on the impact of the EU Semester, the EU Funds and the Recovery & Resilience Plans, on poverty and inequality in the Member States (WP4) |  |  |  | Task 4.2 - Dissemination of main proposals & recommendations of the “Assessment…” reports to target audience
Task 4.3 - Evaluating the annual policy Conference attendee’s satisfaction
Awareness raising and meaningful participation of people living in poverty regarding their rights at national and EU level (WP5) | } | 5 | Engagement and Participation of People Experiencing Poverty | Task 5.1 - Empower people experiencing poverty to analyse, provide input and participate in EU policy making processes |  | Ensure that they are meaningfully involved in, and leading, grassroots anti-poverty advocacy work and campaigns around poverty, inequality, precarious work, digitalisation, social protection (with a focus on minimum income), living wages, at national and European levels. | Developing challenging frames and narratives, and alternative social and economic political options. | Advocate and campaign for social protection systems
Dissemination of key messages regarding social rights coming from people experiencing poverty (WP5) |  |  |  | Task 5.2 - Organize the 2022 Meeting of People Experiencing Poverty
Task 5.3 - Produce the Briefing Paper “Voices from the Ground for a Socially Just EU”
Exchange of good practices on social inclusion, presented by EAPN members and other EU platforms (WP6) | } | 6 | Networking, Training and Advocating for Social Rights at the EU | Task 6.1 - Network capacity building for detecting, selecting, analysing and exchanging good practices |  |  |  | Advocate and campaign for social protection systems (with a focus on minimum income schemes), and living wages throughout Europe, directly towards governments but with an increased focus on the public as well. As part of our advocacy we will continue to push for meaningful civil society space in national and European political processes with the most potential impact on the eradication of poverty and social exclusion. EAPN will focus this advocacy and campaigning firmly on European Institutions and Member States
Training and support for the organizational development and increased awareness about EU policies and funding among EAPN members (WP6) |  |  |  | Task 6.2 - Training and capacity building session on the revised social scoreboard
Needs assessment and capacity building of the membership - policy, advocacy, governance, IT, and organisational development (WP6) |  |  |  | Task 6.3 - Strengthening the organisational capacity of EAPN national network
Task 6.4 - Engagement and joint advocacy in coalitions and alliances
Communication of key messages and positions for the the fight against poverty and social exclusion in Europe (WP7) | } | 7 | Dissemination and Communication | Task 7.1 - Communicating for “social change” |  | We will amplify the voice of individuals and groups living in poverty so that their authentic experience is heard, understood and used by the media, policy makers and the public. | Developing challenging frames and narratives, and alternative social and economic political options. We will develop a compelling narrative about the reality of poverty in Europe, increasing our capacity to translate facts, figures and policies into meaningful and accessible stories that inspire action and aid understanding, to support our policy messages. | Advocate and campaign for social protection systems (with a focus on minimum income schemes), and living wages throughout Europe, directly towards governments but with an increased focus on the public as well. As part of our advocacy we will continue to push for meaningful civil society space in national and European political processes with the most potential impact on the eradication of poverty and social exclusion. EAPN will focus this advocacy and campaigning firmly on European Institutions and Member States
Task 7.2 - Producing and disseminating EAPN publications
Task 7.3 - Design and implementing awareness raising campaigns
Awareness raising about the reality of poverty and EU policies (WP7) |  |  |  | Task 7.4- Supporting EAPN’s members in their communication and dissemination work
Task 7.5 - Developing and disseminating accessible plain language 2 pagers for key EAPN publications
Task 7.6 - Developing EAPN online communication
Note on G19: Priority also applies to WPs 2 and 3
Note on E37: Includes 8 EAPN Flash, 3 with Poverty Alert Section

## ST OBJ_SGA
Priority | Strategic Objectives
| 2 years |  |  |  |  | 5 years
| # | External | WP | Internal | WP | # | External | Internal
A. Policy Expertise | 1 | Influenced EU Institutions to deliver a strong Action Plan to implement the European Pillar of Social Rights, which responds to our advocacy efforts and can be traced, at least in part, to our on all Principles relevant to the fight against poverty on which EAPN will work. | 3 | Developed positions on our key priority themes (In addition to these agreed priorities, we remain attentive to opportunities or (urgent) issues that require our attention and follow up, based on the needs of people experiencing poverty and European policy opportunities) | 2,3,4 | 1 | Strengthened and increased our influence on European Institutions and national governments as key partners in the monitoring/implementation process through the European Semester and other key European policy processes to combat poverty (peer reviews, EU consultations, EU presidency initiatives, EP intergroup on poverty, EP reports on key topics), with the result that at least half of EU Member States get a recommendation to develop an integrated anti-poverty policy.’ | Produce annual Poverty Watches for all EU Member States which inform key EU process such as the EU Semester.
| 2 | Contributed to the implementation of the Action Plan through our policy and advocacy work | 3 | Strengthened the EAPN policy team to ensure that EAPN Europe can act and is recognised as the key stakeholder to keep poverty and social exclusion on top of the EU political agenda. | 2,3,4 | 2 | Influenced EU Institutions to reduce poverty and inequality throughout Europe by ensuring adequate financing by the EU and at national levels, including by a more progressive tax systems | Established a programme of participatory research to complement and feed into policy and advocacy work
| 3 | Supported the members of EAPN in the delivery of a strong action plan and its implementation. In addition to these agreed priorities, we remain attentive to opportunities or (urgent) issues that require our attention and follow up, based on the needs of people experiencing poverty and European policy opportunities | 2,3,4 | Ensured that EAPN does not miss any major opportunity to influence EU policy that impacts directly or indirectly on poverty and social exclusion, by regular monitoring and identification of key political and policy areas on which to focus by the Ex CO, on advice of the EUISG, based on the following criteria |  | 3 |  | Continued strengthening the EAPN policy team
| 4 | Influenced EU Institutions to agree an ambitious poverty goal, strategy and targets at the European level - notably a goal to end poverty in all its forms (SDG1), through a 50% target and an additional indicator/target to cover extreme poverty, including a concrete measurement of homelessness | 3 | Developments that influence the lives of people in poverty |  | 4 |  | Integrated the human-rights based approach to our fight against poverty, including by using international and European human rights treaties in our advocacy, campaigns and legal work.
| 5 | Influenced EU institutions to ensure that EU policies and funding diminish the negative impact from the covid 19-crisis on people experiencing poverty. | 4 | EU policy opportunities (where there is a window to have an actual impact to make a positive change) |  | 5 |  | Strengthened the policy impact of the PeP conference
| 6 | Contributed to the achievement of the Child Guarantee by supporting NNs in monitoring and being involved in the implementation of the Child Guarantee at the national level.’ | 3 | The strategic review |  | 6 |  | Strengthened the involvement of national and European members in the EU advocacy work, for instance through building and using their relations with national governments (who are represented in the Council of the EU), Members of the European Parliament (MEPs) and the national desks of the European Commission.
| 7 | Consistently participated in the Future of Europe conference, ensuring EAPN positions are reflected in the outcome document and that EAPN, its members and people experiencing poverty and organisations representing and working with them are included in the process | 2,3,4 | Made demonstrable progress on gender and race analysis and mainstreaming into our policy work | 2,3,4 | 7 |  | Built the capacity of national members to support their involvement in EU processes and helped them identify opportunities on how this can support their work at the national level.
| 8 | Become the recognised civil society expert on poverty by the EU based on strong policy working, our national Poverty Watches and supporting the members to making use of EU initiatives to support their work at national level | 2 | Strengthened the impact of the annual Policy Conference | 4 | 8 |  | Invested in and organized more EU level events with other organisations, bringing member expertise from the national and EO members, including the European Parliament, Permanent Representations, EESC which are adequately supported and resourced
| 9 |  |  |  |  | 9 |  | Organised exchange of advocacy experiences, policies and practices between the members.
B. Strengthen the involvement of people experiencing poverty | 1 |  |  | Clarified the role of PeP and PeP National Coordinators in EAPN at national and European levels, in order to align its mandate with other groups (Ex Co, Policy Group) | ALL | 1 | Ensured strengthened participation of PeP at the European level in specific processes (Semester, Future of Europe, for example) | Created a funding pot which would allow PeP (in coordination with national networks) to apply for micro-grants to develop campaigns and advocacy actions throughout Europe and to support capacity building (peer learning) on participation.
| 2 |  |  | Supported members to understand and implement, to the degree possible, the Guidelines of EAPN Communication Group |  | 2 | Demonstrated that the highest level of European political leadership takes the findings / recommendations of the PeP meeting into consideration, having better engaged PeP in this advocacy work – for example, organising a small meeting of PeP delegation with leaders, in coordination with the policy work of EAPN | Stood in solidarity, as EAPN Europe, with at least 3 specific campaigns which have been proposed, developed and led by people experiencing poverty (through our members). Concretely, this could mean giving a statement of support, supporting financially, agreeing to communicate in support of the campaign etc.
| 3 |  |  | Ensured that all EAPN structures consider the PeP report, and feedback how they will (and will not) act on it | 5 | 3 |  | Based on a mapping on the needs of national members to support and empower PeP to engage in advocacy work, developed material and trainings which help national networks to build their participation work and engage PeP in national campaigns and advocacy
| 4 |  |  | Built a shared understanding of the concept of meaningful participation of PeP | 5 | 4 |  | Implemented the Guidelines of EAPN’s Communication Group at the European level and supported members to implement the guidelines at national level, to the degree they are found useful by national networks
| 5 |  |  | Developed a mapping of how members organise the participation of PeP |  | 5 |  | Supported 25 national networks to adopt/participate in the journalism prize
| 6 |  |  | Defined guidelines to orient members to organise meaningful participation of PeP at the national and European level |  | 6 |  | Developed and implemented training programs / exchanges / peer reviews in EAPN political areas of work, oriented to PeP, in order to achieve common understanding in some key areas of EAPN, and raised their involvement in policy areas (in close relation to EAPN’s Policy Group)
| 7 |  |  | Built a shared understanding about the journalism prize and its role in promoting the participation of PeP |  | 7 |  | Supported every EAPN national network to organise a national/regional/local PeP meeting(s), and / or have alternative plans / structures to meaningfully engage PeP, or have an action plan to develop this area
| 8 |  |  | Ensured that representatives of EAPN structures contribute, in an integrated and mutual fashion, to the process of defining the theme of the European PeP meeting | ALL | 8 |  | Strengthened the participation of PeP in EAPN Europe’s governing structures
| 9 |  |  | Clarified the link between policy and participation and provided guidelines to structure this, this in cooperation with the EAPN’s Policy Group and the policy team | 2,3,4,5 | 9 |  | Supported our members to strengthen the participation of PeP in their governing structures
| 10 |  |  |  |  | 10 |  | Ensured that EAPN’s policy messages and PeP meeting messages are mutually reinforcing and complementary
| 11 |  |  |  |  | 11 |  | Established a programme of participatory research to complement / feed into policy and advocacy work, in cooperation with the EAPN membership
C. Building public support and pressure for the eradication of poverty and an end to neoliberalism austerity politics | 1 |  |  | Supported all members in their external communication, e.g. website and social media. |  | 1 |  | Ensure that both the experience of PeP and the expertise of organisations working with PEP are central parts of our comms work, which is being delivered in a participatory, bottom up approach, serving the policy and advocacy objectives of EAPN
| 2 |  |  | Develop a realistic communication plan to support the policy and advocacy objectives of EAPN, involving people experiencing poverty where it can be done in a meaningful way. | 7 | 2 |  | Organised a European wide visibility action with strong media coverage, in support of a specific advocacy goal.
| 3 |  |  | Established a library of best practise and comms tools from our members, as a learning tool |  | 3 |  | Developed and regularly used a European level frames and narratives around poverty, and supported at least 10 members to develop and use their own narratives
| 4 |  |  | Improved internal and external communication (in terms of participation of PeP) by disseminating and adapting guidelines of EAPN’s Communication Group. |  | 4 |  | Supported members in finding resources for a dedicated staff focusing on communication and building the capacity of this person (if needed).
| 5 |  |  | Built an understanding how comms and policy work can support and mutually reinforce each other together with the policy team | 2,3,4,6,7 | 5 |  | Developed a social media audience of at least 50 000 people
| 6 |  |  | Identified how national practices and examples from the ground can be better promoted at the EU level in order to support EAPN’s policy and advocacy objectives. | 7 | 6
| 7 |  |  | Mapped the needs of national members in terms of external communication (to identify capacity building and supporting activities) | 6 | 7
| 8 |  |  | Clarified what the aim and the mandate is of the comms work of EAPN Europe is, respecting the independence of the EAPN membership |  | 8
| 9 |  |  | Examined EAPN’s capacity to get involved in public campaigning and building public support. This should include an evaluation of the public campaigning aspect of EMIN 2 and as well an assessment of the capacity of EAPN’s members (financial and human resources, experience and knowledge), and their intentions / motivation to influence public opinion. | 6.7 | 9
| 10 |  |  | Developed a set of short EAPN explainers on systemic issues: tax, wealth, inequality | 2,3,4,7 | 10
D. Advocate and campaign for social protection | 1 | Helped ensure that the Action Plan for the European Pillar of Social Rights provides a framework for Member States to implement adequate, accessible and enabling Minimum Income schemes, and references a Framework Directive | 3, 6 | Secured and started to implement an EMIN3 project with a strong involvement of EAPN members |  | 1 | Influenced the EU Institutions to agree an EU Framework Directive on Minimum Income which meets EAPN standards | Developed, with members and partners, a clear and compelling case for DG Employment and others to strengthen the participation of anti-poverty organisations and people experiencing poverty in civil dialogue, based on Article 11.2 of the Treaty on European Union
| 2 | Influenced EU institutions to translate the 2020 Council Conclusions on Minimum Income into concrete progress on a framework directive and other initiatives to ensure adequate, accessible and enabling minimum income schemes | 2,3,4,6 | Influenced other EU mechanisms and instruments, besides the peer reviews, so they are used to make progress towards adequate, accessible and enabling MIS for all | 2,3,4,6 | 2 | Influenced EU Institutions to establish an EU Framework Directive to guarantee access to social protection to all regardless of employment status, following impact assessment of Council Recommendation on access to social protection for workers and the self-employed
| 3 | Influenced EU Council Presidency countries to keep the issue of Minimum Income high on the political agenda | 2,3,4,6 | Organised internal exchange of policy outcomes and advocacy activities on the topic of minimum income between members. E.g. in Spain important steps have been taken to improve minimum income schemes for people in poverty. It would be interesting to learn more about the policy changes that have been achieved and the advocacy work undertaken by EAPN Spain (as source of inspiration for other members and to promote good practices at the EU level). | 2,3,4,6 | 3
| 4 | Influenced EU Institutions to agree on EU level legislation on minimum / living wages which meets EAPN standards, in partnership with EAPN membership | 2,3,4,6 | Influenced EU Institutions to agree a strong and ambitious implementation plan of the EPSR in relation to principle 14 and other relevant principles to income | 3.6 | 4
| 5 | Participated as experts (EAPN Europe and members) in at least 2 EU peer reviews on minimum income | 2,3,4,6 |  |  | 5
| 6 | Organised internal exchange of policy outcomes and advocacy activities on the topic of minimum income between members. E.g. in Spain important steps have been taken to improve minimum income schemes for people in poverty. It would be interesting to learn more about the policy changes that have been achieved and the advocacy work undertaken by EAPN Spain (as source of inspiration for other members and to promote good practices at the EU level). | 2,3,4,6 |  |  | 6
| 7 | Supported members to monitor and be involved in the EPSR implementation plan on minimum income | 2,3,4,6 |  |  | 7
| 8 |  |  |  |  | 8
| 9 |  |  |  |  | 9
| 10 |  |  |  |  | 10

## Work Programme
WORK PACKAGE |  | ACTIVITY | MONTHS
|  | TASK | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12
1 | General Management and running of the organisation | Task 1.1 - Joint planning and delivery |  |  |  |  | PR Start |  | PR End |  |  | PL Start |  | PL END
|  | Task 1.2 - Monitoring and evaluation | M&E Q4 |  |  | M&E Q1 |  |  | M&E Q2 |  |  | M&E Q3 |  | D 1.1
Task 1.3 - Exploratory study on the usage of digital tools by people experimenting poverty
2 | Multidimensional Poverty and Cross-cutting Factors | Task 2.1 - Comprehensive analysis of the reality of poverty and inequalities in the EU | [8 empty] | D 2.1
|  | Task 2.2 - Dissemination to EU institutions of the information, knowledge and policy recommendations on the challenges faced by vulnerable groups | [9 empty] | D 2.2
Task 2.3 - Communication action to relevant EU institutions of the key results and recommendations of the 2022 Poverty watch
Task 2.4 - Advocacy activities, using the 2022 EU poverty watch
3 | EPSR Implementation | Task 3.1 - Follow up and engagement action on the implementation of the EPSR AP at national and local level | [5 empty] | D 3.1
Task 3.2 - Advocacy actions, supported by the ESPR report
|  | Task 3.3 - Assessment of the 2030 national poverty goal | [10 empty] | D 3.2
4 | European Semester, Structural Funds and Recovery & Resilience Plans | Task 4.1 - Comparative research and capacity building on the governance of the EU Semester, EU Funds and the Recovery and Resilience Plans | [5 empty] | D 4.1
|  | Task 4.2 - Dissemination of main proposals & recommendations of the “Assessment…” reports to target audience |  |  |  |  | D 4.2
Task 4.3 - Evaluating the annual policy Conference attendee’s satisfaction
5 | Engagement and Participation of People Experiencing Poverty | Task 5.1 - Empower people experiencing poverty to analyse, provide input and participate in EU policy making processes
|  | Task 5.2 - Organize the 2022 Meeting of People Experiencing Poverty | [10 empty] | D 5.1
|  | Task 5.3 - Produce the Briefing Paper “Voices from the Ground for a Socially Just EU” | [11 empty] | D 5.2
6 | Networking, Training and Advocating for Social Rights at the EU | Task 6.1 - Network capacity building for detecting, selecting, analysing and exchanging good practices | [11 empty] | D 6.1
Task 6.2 - Training and capacity building session on the revised social scoreboard
Task 6.3 - Strengthening the organisational capacity of EAPN national network
Task 6.4 - Engagement and joint advocacy in coalitions and alliances
7 | Dissemination and Communication | Task 7.1 - Communicating for “social change”
Task 7.2 - Producing and disseminating EAPN publications
|  | Task 7.3 - Design and implementing awareness raising campaigns | [11 empty] | D 7.2
Task 7.4- Supporting EAPN’s members in their communication and dissemination work
|  | Task 7.5 - Developing and disseminating accessible plain language 2 pagers for key EAPN publications | [5 empty] | 2Ps |  |  | 2P |  | 2P
|  | Task 7.6 - Developing EAPN online communication | D 7.1 |  | D 7.1 | D 7.1 |  | D 7.1 | D 7.1 |  | D 7.1 | D 7.1 |  | D 7.1
Note on H6: Discussion on strategic and policy priorities starts (Ex Co and GA, Policy Conference)
Note on J6: Strategic and policy priorities agreed, shaping 2023 SGA application
Note on M6: Discussion on joint planning (SGA 2023) starts (Ex Co and GA, EU Poverty Watch Conference)
Note on O6: Joint planning (SGA 2023) finalised
Note on O7: Annual Project Report The Annual Project Report describes the project’s activities and deliverables and measures the achievement of the objectives. It is the main instrument of management and accountability. It is an electronic document, written in English, with approximately 70-100 pages. It is uploaded to the members’ room on EAPN’s website and submitted to the European Commission.
Note on L10: 2022 EU Poverty Watch (PW) In 2022, the PW will focus on people in poverty collecting benefits, as minimum income, principle 14. The EU PW report is an electronic publication, published in English, extension 50 to 70 pages, with a 2-pager summary to be translated into other languages.
Note on M11: EU Poverty Watch launch Conference Conference will be on-line. The work will include the invitation, agenda, signed presence list. The duration of the event: 5-7 hours. The report of the event will include presentations, evaluation report, and feedback questionnaire.
Note on I15: EPSR Report (“Principles 16, 17 and 18. Health and social assistance systems under strain: coverage and accessibility gaps and the consequences of the pandemic of Covid-19.”) The objectives of the report are: 1) To generate knowledge on the implementation of the Action Plan of the EPSR, at national, and regional levels; and 2) To provide inputs for groups of people in poverty and CSO’s, who fight for their social rights. It will be an electronic document with 40-60 pages, in English, with a 2-pager summary. It will be uploaded to EAPN Website and distributed through social media and the EAPN Flash
Note on N17: Position Paper “The post-pandemic at the EU: a multidimensional approach to poverty eradication” The Position Paper will analyse progress towards the targets of the EPSR Action Plan with the new social scoreboard indicators, and the monitoring of national goals to achieve joint poverty reduction. It will be an electronic document, with 20-30 pages, written in English, and with a 2-pager summary. It will be uploaded to EAPN Website and distributed through social media and the EAPN Flash.
Note on I19: Assessment of the European Semester, the implementation of the EU Funds and the RR Plans The report is an electronic document, written in English, with approximately 50-70 pages. A 2-pager summary will be produced in plain English, for dissemination targeted at people experiencing poverty and the general public. Both documents will be uploaded to EAPN’s Website and distributed through social media and the EAPN Flash.
Note on H20: Annual Policy Conference The Annual Policy Conference will be face-to-face event held in Brussels (approximately 5 - 7h). The work will include the invitation, agenda, and signed presence list. The report of the event will include the concept note, event programme, key findings and recommendations, presentations, and evaluation.
Note on N24: Annual EU Meeting of People Experiencing Poverty 2022 Face-to-face meeting, held in Brussels, with 150 participants. The work will include the invitation, agenda, signed presence list. The event’s duration is 1.5 days. The report of the event will include presentations, evaluation report, feedback questionnaire
Note on O25: Briefing Paper “Voices from the Ground for a Socially Just EU” The “Voices from the Ground for a Socially just EU” is a Briefing Paper, 5-7 pages, written in English. It will be published online. In attention to the digital divide, 50 issues will be printed on paper and sent to the members that asked for them in advance.
Note on O27: Model for Mutual Learning and Organizational Strengthening The Model for Mutual Learning and Organizational Strengthening, which includes the Concept Note for the Benchmarking on Social Inclusion Report, will set EAPN’s criteria to assess the quality of good practices and the correlated objective information to identify them. It is an electronic document, written in English.
Note on O34: Awareness campaign Online campaign to raise awareness and influence specific stakeholders on relevant EU processes and EAPN key positions. The language of the campaign is English and the material (messages, visuals) used are electronic
Note on I36: Development of 2-pagers for the EPSR and EU Semester reports (D 3.1 / D 4.1)
Note on L36: Development of 2-pagers for the EU Poverty Watch Report (D 2.1)
Note on N36: Development of 2-pagers for the Position Paper (D 3.2)
Note on C37: Includes 8 EAPN Flash, 3 with Poverty Alert Section
Note on D37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on F37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on G37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on I37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on J37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on L37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on M37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.
Note on O37: EAPN FLASH 8 EAPN Flash published per year, 3 with a “Poverty Alert'' section This section will help flag emerging challenges in the fight against poverty and make policy proposals to EU and National governments. The Flash is an electronic publication, written in English, and disseminated online and by subscription.

## Budget per Work Package
Budget by work Package
WP | A. Personnel |  | B. Subcontracting | C.1a Travel |  | C.1b Accomodation | C.1c Subsistence | C.2 Equipment | C.3 Other goods, works and services | D.1 Financial support to third parties | E. Indirect costs (n/a for OG) | Total costs
1 | 15,92 PM | 116300.27 | 8900 | 73 persons travelling | 16060 | 19395 | 4747.5 | 8171.43 | 43078.57 | 0 | n/a | 216652.77
2 | 16,20 PM | 89840.46 | 0 | 30 persons travelling | 6600 | 8100 | 1800 | 1071.43 | 43568.57 | 0 | n/a | 150980.46
3 | 13,58 PM | 65879.16 | 0 | 0 persons travelling | 0 | 0 | 0 | 1071.43 | 14618.57 | 0 | n/a | 81569.16
4 | 13,94 PM | 85779.27 | 2000 | 32 persons travelling | 7040 | 8460 | 1880 | 1071.43 | 69218.57 | 0 | n/a | 175449.27
5 | 21,46 PM | 112182.1 | 0 | 370 persons travelling | 53900 | 46600 | 12300 | 4571.43 | 149418.57 | 0 | n/a | 378972.1
6 | 12,08 PM | 68340.35 | 2500 | 3 persons travelling | 660 | 540 | 120 | 1071.43 | 14818.57 | 0 | n/a | 88050.35
7 | 13,86 PM | 68581.87 | 2500 | 3 persons travelling | 660 | 540 | 120 | 1071.43 | 19568.57 | 0 | n/a | 93041.87
|  | 606903.48 | 15900 |  | 84920 | 83635 | 20967.5 | 18100.01 | 354289.99 | 0 |  | 1184715.98

## Staff Effort per Work Packages
Distribution of staff effort between work packages
Name | Position | TOTAL DAYS | WP1 |  | WP2 |  | WP3 |  | WP4 |  | WP5 |  | WP6 |  | WP7 |  | TOTAL
|  |  | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS | % TIME | DAYS
Helder Ferreira | Interim Director | 210 | 50% | 105 | 7.5% | 15.75 | 7.5% | 15.75 | 10% | 21 | 7.5% | 15.75 | 10% | 21 | 7.5% | 15.75 | 100% | 210
Philippe Lemmens | Finance/admin. | 210 | 50% | 105 | 12.5% | 26.25 | 0% | 0 | 12.5% | 26.25 | 25% | 52.5 | 0% | 0 | 0% | 0 | 100% | 210
Elke Vandermeerschen | Communication | 180 | 0% | 0 | 5% | 9 | 2.5% | 4.5 | 2.5% | 4.5 | 10% | 18 | 10% | 18 | 70% | 126 | 100% | 180
Magda Tancau | Development/Participation | 225 | 0% | 0 | 10% | 22.5 | 0% | 0 | 0% | 0 | 70% | 157.5 | 20% | 45 | 0% | 0 | 100% | 225
Kahina Rabahi | Policy and Advocacy Coordinator | 225 | 0% | 0 | 7.5% | 16.875 | 7.5% | 16.875 | 60% | 135 | 2.5% | 5.625 | 20% | 45 | 2.5% | 5.625 | 100% | 225
Sabrina Iannazzone | Policy Officer 1 | 225 | 0% | 0 | 7.5% | 16.875 | 70% | 157.5 | 7.5% | 16.875 | 0% | 0 | 15% | 33.75 | 0% | 0 | 100% | 225
TBC | Policy Officer 2 | 225 | 0% | 0 | 70% | 157.5 | 15% | 33.75 | 5% | 11.25 | 0% | 0 | 10% | 22.5 | 0% | 0 | 100% | 225
Rebecca Lee | Events Officer | 225 | 10% | 22.5 | 10% | 22.5 | 5% | 11.25 | 10% | 22.5 | 20% | 45 | 15% | 33.75 | 30% | 67.5 | 100% | 225
Sigrid Dahmen | Office Manager | 132 | 50% | 66 | 12.5% | 16.5 | 0% | 0 | 12.5% | 16.5 | 25% | 33 | 0% | 0 | 0% | 0 | 100% | 132
TBC | Stagiaires | 150 | 0% | 0 | 0% | 0 | 10% | 15 | 5% | 7.5 | 50% | 75 | 5% | 7.5 | 30% | 45 | 100% | 150
|  |  |  | 298.5 |  | 303.75 |  | 254.625 |  | 261.375 |  | 402.375 |  | 226.5 |  | 259.875 |  | 2007

## PM calculation
Name | Function | Person months 2022 | Days | Hours | Amount / day in Euro | Total in Euro | Check Total in Euro | Amount per PM | Check PM total
TBC | director | 11.2 | 210 | 1596 | 420.95 | 88399.5 | 88399.5 | 7892.8125 | 88399.5
Philippe Lemmens | Finance/admin. | 11.2 | 210 | 1596 | 390.48 | 82000.8 | 82000.8 | 7321.5 | 82000.8
Elke Vandermeerschen | Communication | 9.6 | 180 | 1368 | 327.78 | 59000.4 | 59000.4 | 6145.875 | 59000.4
Magda Tancau | Development/ Participation | 12 | 225 | 1710 | 328.89 | 74000.25 | 74000.25 | 6166.6875 | 74000.25
Kahina Rabahi | Policy and Advocacy Coordinator | 12 | 225 | 1710 | 337.78 | 76000.5 | 76000.5 | 6333.375 | 76000.5
Sabrina Iannazzone | Policy Officer 1 | 12 | 225 | 1710 | 255.56 | 57501 | 57501 | 4791.75 | 57501
TBC | Policy Officer 2 | 12 | 225 | 1710 | 255.56 | 57501 | 57501 | 4791.75 | 57501
Rebecca Lee | Events Officer | 12 | 225 | 1710 | 271.11 | 60999.75 | 60999.75 | 5083.3125 | 60999.75
Sigrid Dahmen | Office Manager | 7.04 | 132 | 1003.2 | 378.79 | 50000.28 | 50000.28 | 7102.3125 | 50000.28
TBC | Stagiaires | 8 | 150 | 1140 | 10 | 1500 | 1500 | 187.5 | 1500
Total staff |  | 107.04 | 2007 | 15253.2 |  | 606903.48 | 606903.48 |  | 606903.48